## Sheet1
PETSMART PREPARATION CHECKLIST
PETSMART - STORE #
PLEASE CHECK THESE KEY ITEMS TO ENSURE BALANCING CAN PROCEED SMOOTHLY
| RTU-1 | RTU-2 | RTU-3 | RTU-4 | RTU-5 | RTU-6 | RTU-7 | RTU-8 | EF-1 | EF-2 | EF-3 | EF-4
Ductwork is 100% Completed/All terminals installed
All inlets/outlets have balancing dampers
All balancing dampers are accessible
Ductwork and diffusers are insulated as per spec
Wet area diffusers are insulated (blanket on top)
Plenum Boxes for linears are insulated
Filters are installed
HVAC units are installed in proper locations
Exhaust fans are installed in proper locations
HVAC Systems and exhaust fans are wired
HVAC Systems have been started up
Overload protection is properly sized
Outside air damper controls are operational
PLEASE CHECK OFF EACH ITEM AS IT IS VERIFIED COMPLETED AND RETURN CHECKLIST ONCE COMPLETED
PLEASE ENSURE THE MOTORIZED DAMPERS ARE INSTALLED AND OPERATIONAL ON RTU-5 (HOLDING ROOM)
THESE ARE THE MOST OVERLOOKED ITEM - PLEASE DOUBLE CHECK